## chatbot test
No | Task Name | Sub Module | Functionality | Result | Remarks | Remarks (25/8/2025) | Remarks (21/8/2025) | Remarks (20/8/2025) | Remarks (19/8/2025) | Remarks (15/8/2025)
General
RAG - Documents
|  |  | Chat to PDF - One Document - Category 1 | Failed | Bot failed to answer when asked for the "recipe" due to absence of the word in the document. However, it correctly answered the paraphrased prompt "how to make...". Refer img 1. (based on the old ver) | Bot failed to answer when asked for the "recipe" due to absence of the word in the document. However, it correctly answered the paraphrased prompt "how to make...". Refer img 1. (based on the old ver) | Bot failed to answer when asked for the "recipe" due to absence of the word in the document. However, it correctly answered the paraphrased prompt "how to make...". Refer img 1. (based on the old ver) | Bot failed to answer when asked for the "recipe" due to absence of the word in the document. However, it correctly answered the paraphrased prompt "how to make...". Refer img 1. (based on the old ver) | Bot failed to answer when asked for the "recipe" due to absence of the word in the document. However, it correctly answered the paraphrased prompt "how to make...". Refer img 1. | Bot failed to answer when asked for the "recipe" due to absence of the word in the document. However, it correctly answered the paraphrased prompt "how to make...". Refer img 1.
[5 empty] | The pdf contains two short stories but the bot only able to retrieve one story from that one document. Refer img 2. | The pdf contains two short stories but the bot only able to retrieve one story from that one document. Refer img 2. | The pdf contains two short stories but the bot only able to retrieve one story from that one document. Refer img 2. | The pdf contains two short stories but the bot only able to retrieve one story from that one document. Refer img 2.
[5 empty] | Asking a question about the uploaded document but answer with something that is not in the document library. Refer img 3. | Asking a question about the uploaded document but answer with something that is not in the document library. Refer img 3. | Asking a question about the uploaded document but answer with something that is not in the document library. Refer img 3. | Asking a question about the uploaded document but answer with something that is not in the document library. Refer img 3.
|  |  | Chat to PDF - Multiple Documents - Same Category 1 | Failed | Could not retrieve some of the uploaded documents. Mixing up the content with previous uploaded documents. | Could not retrieve some of the uploaded documents. Mixing up the content with previous uploaded documents. | Could not retrieve some of the uploaded documents. Mixing up the content with previous uploaded documents. | Could not retrieve some of the uploaded documents. Mixing up the content with previous uploaded documents. | can retrieve data from multiple documents | can retrieve data from multiple documents
|  |  | Chat to DOCX - One Document - Category 2 | Failed | Asking a question about the uploaded document but answer with something that is not in the document library. | Asking a question about the uploaded document but answer with something that is not in the document library. | Asking a question about the uploaded document but answer with something that is not in the document library.
|  |  | Chat to DOCX - Multiple Documents - Same Category 2 | Failed | Unable to retrieve the uploaded documents. When asked, bot answered with documents that are not in the document library. | Unable to retrieve the uploaded documents. When asked, bot answered with documents that are not in the document library. | Unable to retrieve the uploaded documents. When asked, bot answered with documents that are not in the document library. |  |  | will test next week
|  |  | Chat to DOCX - Outside DOCX Content | Failed | Unable to verify this due to error in retrieving contents from the uploaded documents. | Unable to verify this due to error in retrieving contents from the uploaded documents. | Unable to verify this due to error in retrieving contents from the uploaded documents. |  |  | will test next week
|  |  | Chat to TXT - Multiple Documents - Same Category 3 | Failed | Upload second documents with similar category, but when asked with similar questions as the first document, the bot could not answer | will test tomorrow
|  |  | Chat to TXT - Outside TXT Content | N/A |  | will test tomorrow
|  |  | Chat to CSV - One Document - Category 4 | Failed | Unable to retrieve the contents of the data, only able to summarize the whole points. Refer img 9. | Unable to retrieve the contents of the data, only able to summarize the whole points. Refer img 9. | Does not allow uploading blank document | Does not allow uploading blank document | sometimes it answered by refering to pdf file that has been deleted | sometimes it answered by refering to pdf file that has been deleted
|  |  | Chat to Blank CSV | Failed | Allows to upload blank CSV file | Allows to upload blank CSV file
|  |  | Delete All documents (PDF , DOCX , TXT , CSV ) and then Chat | Failed | Able to answer based on previous deleted documents | will test tomorrow
Form Generator
|  |  | Edit Company | Failed | Unable to edit company name (this happened after saving the logo but okay when edit the name first) and unable to delete the logo after saving
|  |  | Submit Form | Failed | Able to submit even when required fields is not filled in
|  |  | Clear All Data | Failed | Button not functioning
|  |  | Save Progress | Failed | Button not functioning
API Executer
API
|  |  | API - Web Search | Failed |  | Failed to return data. Shows raw code. Refer img 6. | Failed to return data. Shows raw code. Refer img 6. |  | there is no options to add API
|  |  | API - Date/Time | Failed | Date/Time tool is not functioning but instead it fall back to Web Search (which is not working). Refer img 5. | Date/Time tool is not functioning but instead it fall back to Web Search (which is not working). Refer img 5. | Date/Time tool is not functioning but instead it fall back to Web Search (which is not working). Refer img 5. |  | there is no options to add API
Analytics - System analytics & data insights
|  |  | System statistics | Failed | Able to summarize reports/system statistics but hard to read due to messy format, refer img 10 | "Failed to load analytics"
Escalation - Human support & ticket management
Support Chat
|  |  | Request for support | Failed | Not functioning | Not functioning |  |  | unable to prompt the bot to create a live meeting | unable to prompt the bot to create a live meeting